**Work Plan BREAKDOWN STRUCTURE**

|  |  |  |  |
| --- | --- | --- | --- |
| Project Name | CSC Project | Date | 21/3/2022 |
| Team Number | 5 | Document Number | 1 |
| Project Manager | Doaa Sayed | Project Owner/Client | CSC Brand |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS Code /ID | | | | Task Name | | Duration | Dependency | Status |
| 1. |  |  |  | | **Planning** | **19 days** |  | **Open** |
|  | 1.1 |  |  | | Dependencies and constrains | 4 days |  | Completed |
|  | 1.2 |  |  | | System request | 4 days |  | Completed |
|  | 1.3 |  |  | | Technical feasibility | 6 days | 1.1 | Open |
|  |  | 1.3.1 |  | | Economic feasibility | 8 days |  | Open |
|  |  | 1.3.2 |  | | Organizational feasibility | 4 days |  | Open |
| 2. |  |  |  | | **Analysis** | **11 days** | **1.** | **Open** |
|  | 2.1 |  |  | | Conduct interviews of key personnel | 5 days |  | Open |
|  | 2.2 |  |  | | Administer questionnaires | 4 days |  | Open |
|  | 2.3 |  |  | | Read company reports | 4 days |  | Open |
|  | 2.4 |  |  | | Analyze data flow | 2 days | 1.3 | Open |
| 3. |  |  |  | | **Design** | **26 days** |  | **Open** |
|  | 3.1 |  |  | | Scope Definition | 4 days | 1.2 | Open |
|  | 3.2 |  |  | | Researching the latest web design trends | 6 days |  | Open |
|  | 3.3 |  |  | | **Choosing platform** | 2 days | 1.3.1 | Open |
|  | 3.4 |  |  | | Adding in and optimizing content | 8 days |  | Open |
|  | 3.5 |  |  | | Preparing design prototype | 10 days |  | Open |
|  | 3.6 |  |  | | Analyzing and improving | 6 days |  |  |
| 4. |  |  |  | | **Implementation** | **26 days** | **1.3** | **Open** |
|  | 4.1 |  |  | | Prepare the Database | 10 days |  | Open |
|  |  | 4.1.1 |  | | Coding | 10 days |  | Open |
|  |  | 4.1.2 |  | | Testing | 6 days |  | Open |
|  |  | 4.1.3 |  | | Prototyping | 10 days |  | Open |
| 5. |  |  |  | | **Feedback about Prototype Task** | **3 days** | **4.1.3** | **Open** |
|  | 5.1 |  |  | | Collect feedback from focus group | 3 days |  | Open |
| 6. |  |  |  | | **Maintenance and Repair** | **3 days** | **5.** | **Open** |
|  | 6.1 |  |  | | Edit prototype | 2 days |  | Open |
|  | 6.2 |  |  | | Installation | 1 days |  | Open |
| 7. |  |  |  | | **Deals & contracts** | **17 days** | **1. & 2.** | **Open** |
|  | 7.1 |  |  | | Deal with a law firm | 3 days |  | Open |
|  |  | 7.1.1 |  | | Contract with Shipping Company | 3 days |  | Open |
|  |  | 7.1.2 |  | | Contract with Advertising Company | 2 days |  | Open |
|  |  | 7.1.3 |  | | Deals with suppliers | 3 days |  | Open |